## Slide 1
Automotive SoftwareCo – Project Workplan
Jan
Feb
Mar
Week 0
1
2
3
4
5
6
Model Setup + Driver Tree
Competitive Roadmaps
Survey Execution
Today
Zoom on Key Markets
Survey Analysis
Global Archetypes and Key Players
Data and Assumption Gathering
DMS Product Overview
Driver Testing + Iteration
Executive Survey Setup
Competitive Landscape
Survey / Qual. Data Gathering
Auto SoftwareCo Product Suite Overview
Product
Market Model
Strategic Initiative Development
Synthesis / Recommendation
High Level Costing / SOP
Implementation Plan / Roadmap
Workstream
Customer Archetypes